## Sheet1
System Name: ParkTrack CIT
Members: Jhudiel Adrian Artezuela, Jesson Chyd Cultura, Harold Destura
Status: |  | To-do
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Cover Page | Cultura | 2024-08-21 | 2024-08-31 | Done
2. Functional Requirements
2.1 Document Purpose | Artezuela | 2024-08-31 | 2024-09-02 | Done
2.2 Document Scope | Artezuela | 2024-08-31 | 2024-09-02 | Done
2.3 Document Audience | Artezuela | 2024-08-31 | 2024-09-02 | Done
2.4 Business Analysis Approach | Artezuela | 2024-08-31 | 2024-09-02 | Done
2.5 Platform Overview and System Components | Cultura | 2024-08-21 | 2024-08-02 | Done
2.6 Features | Cultura | 2024-08-21 | 2024-08-02 | Done
3. Gantt Chart | Destura | 2024-08-21 | 2024-12-02 | Done
4. Creating Data Models
4.1. Creating Conceptual Data Model | Destura | 2024-08-28 | 2024-08-29 | Done
4.2. Creating Logical Data Model | Cultura | 2024-08-28 | 2024-08-29 | Done
4.3. Creating Physical Data Model | Cultura | 2024-08-30 | 2024-09-01 | Done
5. Github
5.1 Creating of Repository in Github | Cultura | 2024-09-23 | 2024-09-23 | Done
6. Creating UI/UX design using Figma
6.1 Login | Cultura | 2024-09-23 | 2024-10-07 | Done
6.2 HomePage | Cultura | 2024-09-23 | 2024-10-07 | Done
6.3 Menu | Cultura | 2024-09-23 | 2024-10-07 | Done
6.4 Sticker Management Page | Artezuela | 2024-09-23 | 2024-10-07 | Done
6.5 Parking Reservation Page | Destura | 2024-09-23 | 2024-10-07 | Done
6.6 Account Settings | Artezuela | 2024-09-23 | 2024-10-07 | Done
6.7 News | Destura | 2024-09-23 | 2024-10-07 | Done
6.8 Parking Map | Cultura | 2024-09-23 | 2024-10-07 | Done
6.9 ERD | Artezuela | 2024-09-23 | 2024-10-07 | Done
6.10 Updating ERD | Cultura | 2024-10-31 | 2024-11-01 | Done
7. Django Progress Checking 1
7.1 Register, Log in, User API | Cultura | 2024-11-01 | 2024-11-05 | Done
7.2 Vehicle, Sticker API | Artezuela | 2024-11-01 | 2024-11-05 | Done
7.3 ParkingArea, ParkingLot API | Destura | 2024-11-01 | 2024-11-05 | Done
8. Django Progress Checking 2
8.1 Register, Log in UI | Cultura | 2024-11-19 | 2024-11-22 | Done
8.2 Homepage, Menu UI | Cultura | 2024-11-19 | 2024-11-22 | Done
8.3 Parking Reservation UI | Destura | 2024-11-19 | 2024-11-22 | Done
8.4 Account Settings UI | Destura | 2024-11-19 | 2024-11-22 | Done
8.5 Sticker Management UI | Artezuela | 2024-11-19 | 2024-11-22 | Done
9. Adjustments
9.1 Modifying the parking area status to be real-time | Destura | 2024-11-26 | 2024-11-29 | Done
9.2 Adding renew and equip api in sticker management page | Artezuela | 2024-11-26 | 2024-11-29 | Done
9.3 Created and linked the Parking Map | Cultura | 2024-11-26 | 2024-11-29 | Done
9.4 Created admin-side to control the parking area status | Destura | 2024-11-26 | 2024-11-29 | Done
10. Finalizing
10.1 Merging of codes | Cultura | 2024-11-30 | 2024-12-01 | Done
10.2 Finalizing UI design | Destura | 2024-11-30 | 2024-12-01 | Done
11. Final Presentation |  | 2024-11-02 |  | To-do